## Outstanding data
| STATUS | Main Frame | Age | Gender | Source | Qualifications
IWEGA | Outstanding | Mitigation
CSIR |  |  |  | For 2 participants | For all participants | For 5 participants - last course
UWC | Outstanding |  |  | For 2 participants | For all participants | For 5 participants - last course
ZAMBIA | Outstanding | Current status, challenges, challenges highlight & mitigation
BOTSWANA
MALAWI | Complete
KNUST | Outstanding | Data (%) | 28 participants |  |  | 28 participants
NWRI | Outstanding | Data, mitigation | 11 participants | For one course |  | 11 participants
BENIN | Complete
UCAD | Outstanding | Mitigation |  |  |  | 9 participants (2de course)
KHARTOUM | Complete
MAKERERE | Complete
EIWR | Outstanding | Mitigation
ICPAC | Outstanding | Challenges highlight, mitigation

## Main frame
| ACTIVITIES | INDICATOR | DATA | [13 empty] | CURRENT STATUS | [13 empty] | CHALLENGES Y/N | [13 empty] | CHALLENGES HIGHLIGHT | [13 empty] | MITIGATION | [12 empty] | ADDITIONAL COMMENTS
|  |  | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | BOTSWANA | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | BOTSWANA | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | BOTSWANA | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | BOTSWANA | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | KNUST | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR
OBJECTIVE 1 | Prepare the National Framework into an information package for dissemination partners and stakeholders (pamphlet, report,PPT etc.) | An information package was developed | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | COMPLETED | UNDERWAY | COMPLETED |  | UNDERWAY | UNDERWAY | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | YES | NO |  | NO | YES | YES | NO | NO | YES | NO | NO | YES | NO |  | ADMINISTRATIVE |  |  |  | FINANCIAL, FORCE MAJEURE | ADMINISTRATIVE |  |  | FINANCIAL |  |  | FINANCIAL, CONTRACT | [6 empty] | Engaged a designer, sent the a soft copy of the entire framework as was submitted | There was no challenge in the dissemination | No significant challenges encountered during the development of the National framework | Filling the gap through use of personal resources in order to prevent delay in production of results |  | Utilization o institutional funds before receiving transfer from UNESCO | Utilization o institutional funds before receiving transfer from UNESCO | [5 empty] | A report of the strategy was circulated to stakeholder. We did not develop a specific information package |  |  |  | Coopearation and availability of the administration of the Water Sector (changing ministry and governing board, challenge of organizing the World Water Forum in 2021) |  | Limited working period to execute the activities
| Disseminate the strategy to national training institutions? | Nr of national training institutions receiving the information package | 9 | 2 | 2 |  | 3 | 3 | 0 | 8 | 18 | 40 | 5 | 18 | 2 | 6 | UNDERWAY | UNDERWAY | COMPLETED |  |  | COMPLETED | UNDERWAY | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | UNDERWAY | COMPLETED | YES | YES | NO |  |  | YES | YES | NO | NO | YES | NO | NO | YES | NO | OTHER | ADMINISTRATIVE |  |  |  | FORCE MAJEURE | ADMINISTRATIVE |  |  | FINANCIAL, FORCE MAJEURE |  |  | ADMIN |  | Use email to send the dissemination materials and respond to queries anf further information |  |  |  |  | Sent the a soft copy of the entire framework | There was no challenge in the dissemination | No significant challenges encountered during the dissemination of the information package | Planning and making personal financial sacrifices pending fund release. |  | The activity will be completed when a central workshop is organized. This was pushed to the week starting 1st November 2020 | The activity will be completed when a central workshop is organized. This was pushed to the week starting 1st November 2020 | [9 empty] | Difficulties in accessing private training institutions. Other trainings sometimes reluctant to open up to innovations |  | Will be completed in early November
| Disseminate the strategy to other stakeholders? | Nr of other stakeholders receiving the information package | 21 |  | 2 |  | 2 | 5 | 0 | 8 | 36 | 80 | 8 | 20 | 10 | 18 | COMPLETED | COMPLETED | COMPLETED |  |  | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED |  | COMPLETED | YES | YES | NO |  |  | YES | YES | NO | NO | YES | NO | NO | YES | NO | OTHER | OTHER |  |  |  | FORCE MAJEURE | ADMINISTRATIVE |  |  | FINANCIAL |  |  | ADMIN |  | Use email to send the dissemination materials and respond to queries anf further information |  |  |  |  | Sent the a soft copy of the entire framework | there was no challenge in the dissemination | No significant challenges were encountered |  |  | Reprogramming to the convenience of some stakeholders and key actors | Reprogramming to the convenience of some stakeholders and key actors | [11 empty] | Activity will be completed next week
| Based on the strategy and on the implementation framework, prepare at least 2 courses or curricula adaptation and/or modules for Higher Education training for Junior and Senior professionals | Nr of courses/modules developed | 2 | 2 | 9 | 1 | 1 | 2 | 2 | 2 | 10 | 2 | 4 | 3 | 4 | 2 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | UNDERWAY | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | YES | NO | YES | YES | YES | NO | NO | NO | NO | NO | NO | YES | NO |  | FINANCIAL |  | FINANCIAL | FORCE MAJEURE | FINANCIAL | [6 empty] | CONTRACT |  |  |  |  | In-kind contributions |  | These were already sent | Course materials are been developed | No significant challenges as course modules developed successfully |  |  | Through further engagement, UNESCO agreed to allow one course to be implemented in Uganda | Through further engagement, UNESCO agreed to allow one course to be implemented in Uganda | [5 empty] | COVID-19 led to delays in implementation however material was developed. |  |  |  | On certain themes, difficulties in finding specialists able to deliver courses |  | The agreed course was mounted
| Deliver at least 2 pilot courses/modules for junior and/or senior professionals | Nr of courses/modules implemented | 0 | 1 | 3 | 1 | 0 | 2 | 0 | 1 | 6 | 0 | 3 | 2 | 1 | 0 | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | UNDERWAY | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | YES | YES | NO | YES | YES | NO | YES | YES | YES | YES | YES | NO | YES | YES | FORCE MAJEURE | FINANCIAL |  | FINANCIAL | FORCE MAJEURE |  | OTHER | FINANCIAL | FINANCIAL | FINANCIAL, FORCE MAJEURE | HUMAN RESOURCES |  | CONTRACT, HUMAN RESOURCES | CONTRACT |  |  |  | In-kind contributions |  | Done | Procurement process has started to set up eStudio for online training, | Process of engaging partners to increase sporsorship of participants is ongoing |  | Procurement process has started to set up eStudio for online training, | Greenlight was later given by UNESCO which enable us to initiate and implement the course | Greenlight was later given by UNESCO which enable us to initiate and implement the course | The cousres were cancelled |  |  |  |  | Deliver was not possible within the period of reporting. |  |  |  | Unavailability of some teachers who had committed to specific modules and who preferred to abandon the project because of COVID-19 |  | No additionl comment
| Based on the strategy and on the implementation framework, prepare at least 2 courses or curricula adaptation and/or modules for vocational training for junior and senior technicians including education material | Nr of courses/modules developed | 2 | 2 | 3 | 1 | 1 | 2 | 2 | 4 | 10 | 2 | 1 | 3 | 1 | 2 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | UNDERWAY | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | UNDERWAY | COMPLETED | NO | YES | NO | YES | YES | NO | NO | YES | YES | YES | YES | NO | YES | NO |  | FINANCIAL |  | FINANCIAL | FORCE MAJEURE |  |  | FINANCIAL | FORCE MAJEURE | FINANCIAL | HUMAN RESOURCES |  | n/a |  |  |  |  | In-kind contributions |  | Done | Two HND programmes were submitted to National Accreditation and panel report received, (see course details in the attached HCD strategy report) | Based on the covid-19 outbreak, the team adjusting to working from home |  | Human Resources & Sanitary constrainsts | Not applicable | Not applicable | [5 empty] | Deliver was not possible within the period of reporting. |  |  |  | Same as previous comment |  | No comment
| Deliver at least 2 courses/modules for junior and/or senior technicians | Nr of courses/modules implemented | 0 | 1 | 3 | 1 | 0 | 2 | 0 | 0 | 6 | 0 | 1 | 2 | 0 | 2 | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | UNDERWAY | COMPLETED | UNDERWAY | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | YES | YES | NO | YES | YES | NO | YES | YES | YES | YES | YES | NO | YES | NO | FORCE MAJEURE | FINANCIAL |  | FINANCIAL | FORCE MAJEURE |  | FORCE MAJEURE | FINANCIAL | OTHER | FINANCIAL, FORCE MAJEURE | HUMAN RESOURCES |  | CONTRACT, ADMINISTRATIVE |  |  |  |  | In-kind contributions |  | Done | Course materials are been developed | Low sponsorship from the side of engaing partners/agencies. National Water Resources Institute is in the process of engaging partners to increase sporsorship of participants | Staying actions on some of the activities that have security risks | The course materials have been well developed | The course was shelved | The course was shelved | [5 empty] | Deliver was not possible within the period of reporting. |  | time to undertake the training was short, | The Covid-19 pandemic, political uprising in sounthern Nigeria by youths and Insecurity have affected implementeation of the activites. | Same as previous comment |  | If funds become available in future, it will be implemented
OBJECTIVE 2 | Purchase and use of Software, Tools and Consumables for courses/modules and labs | % of items purchased and used | 0% | 100% | 0% | 100% | 0% | 100% | 0% |  |  | 0% | 60% | 100% | 10% | 50% | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED |  | COMPLETED | NOT STARTED | UNDERWAY | UNDERWAY | NOT STARTED | UNDERWAY | COMPLETED | UNDERWAY | COMPLETED | NO | YES | NO | NO |  | YES | YES | YES | YES | YES | YES | NO | YES | YES |  | FINANCIAL |  |  |  | Delays procurement and delivery | OTHER | FINANCIAL | FINANCIAL | FINANCIAL, FORCE MAJEURE | FINANCIAL |  | CONTRACT, ADMIN | CONTRACT | [5 empty] | Used in stock chemicals and instruments to be replaced while awaiting the delivery | Procurement process has started to set up eStudio for online training, | Procurement process ongoing |  |  | We implemented an existin agreement (Framework purchase) between Makerere University and the supplier to atleast obtain a Laptop Computer | We implemented an existin agreement (Framework purchase) between Makerere University and the supplier to atleast obtain a Laptop Computer | Equipment were purchased and used only for the the two TVET level technical courses | [6 empty] | fund for the procurement of eStudio equipment was not available, | The Covid-19 pandemic, political uprising in sounthern Nigeria by youths and Insecurity have affected implementeation of the activites. |  |  | If an opportunity arises to implement the other three courses prioritized, then softwares and materials can be further procured
OBJECTIVE 4 | Undertake a quality review of the course outcomes with Staff and Student participation | Has a quality review taken place for each course? | NO | YES | NO | YES | NO | NO | NO | YES | YES | NO | NO | YES | NO | YES | NOT STARTED | COMPLETED | UNDERWAY | COMPLETED | NOT STARTED | NOT STARTED | UNDERWAY | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTER | COMPLETED | NOT STARTED | COMPLETED | NO | YES | NO | YES |  | NO | NO | NO | NO | YES | YES | NO | YES | NO |  | OTHER |  | CONTRACT |  |  |  | FORCE MAJEURE |  | FINANCIAL, FORCE MAJEURE | ADMINISTRATIVE |  | ADMIN |  |  |  |  | Internal due process followed at CoE |  | Quality review to be undertaken after examinations in December | CoE has undertake the review survey | No significant challenge was encountered |  |  | Not yet planned | Not yet planned |  |  | The quality review is a continuos process, but due to COVID 19 this process needed to be with care to avoid contamination. All the process was done in hardcopy with increase risk |  | Requirements were not stipulated at project inception and planning |  | Quality review to be undertaken after examinations in December |  |  |  |  | Quality review takes a cycle | Only for the the two technical cousres
|  | Nr of Staff consulted in the review? | 0 | 6 | 5 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 12 | 12 | 0 | 3 | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | UNDERWAY | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | UNDERWAY | COMPLETED | UNDERWAY | COMPLETED | NO | YES | NO | YES |  | NO | NO | NO | YES | YES | YES | NO | YES | NO |  | ADMINISTRATIVE |  | CONTRACT |  |  |  | course facilitators and experts have reviewed the course, | OTHER | FINANCIAL, FORCE MAJEURE | ADMINISTRATIVE |  | ADMIN |  |  |  |  | Internal due process followed at CoE |  | Quality review to be undertaken after examinations in December | CoE has undertaken the quality review survey | Due to the outbreak of covid-19 officers from level 12 and below were instructed to stay at home. Preparations for evaluation of staff ongoing |  |  | Administered and awaiting feedback | Administered and awaiting feedback |  |  | The quality review is a continuos process, but due to COVID 19 this process needed to be with care to avoid contamination. All the process was done in hardcopy with increase risk |  | Requirements were not stipulated at project inception and planning |  | Quality review to be undertaken after examinations in December |  |  | This is the number of staff actually consulted with results and real involvement in the . The total number involved exceeds eight |  | Feedback from participants on the trainingreceived | Only for the the two technical cousres
|  | Nr of students included in the review? | 0 | 40 | NO | NO | 0 | 0 | 0 | 34 | 45 | 0 | 21 | 81 | 15 | 10 | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | UNDERWAY | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTER | COMPLETED | UNDERWAY | COMPLETED | NO | YES | NO | YES |  | NO | NO | NO | NO | YES | YES | NO | YES | NO |  | ADMINISTRATIVE |  | CONTRACT |  |  |  | participant did evaluation of the training (see results attached) |  | FINANCIAL, FORCE MAJEURE | FORCE MAJEURE |  | ADMIN |  |  |  |  | Internal due process followed at CoE |  | Quality review to be undertaken after examinations in December | CoE has undertaken the quality review survey | No significant challenge was encountered |  |  | Adminsitered electronically | Adminsitered electronically |  |  |  |  | Requirements were not stipulated at project inception and planning |  | Quality review to be undertaken after examinations in December |  |  | Mixed difficulties related to the health situation, reluctance with respect to mixed teaching and restrictions on campus |  | No additional comment | Only for the the two technical cousres

## Main frame tables
| INDICATOR | DATA | [12 empty] | CURRENT STATUS
|  | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR
OBJECTIVE 1 Dissemination of the strategy to stakeholders, donors and training institutions at national level | Information package developed | YES | YES | YES | YES | NO | YES | YES | YES | YES | YES | YES | YES | YES | COMPLETED | UNDERWAY | UNDERWAY |  | UNDERWAY | UNDERWAY | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED
| Nr. of national training institutions receiving information package | 9 | 2 | 2 |  | 3 | 3 | 8 | OTHER | 40 | 5 | 18 | 2 | 6 | UNDERWAY | UNDERWAY |  |  |  | COMPLETED | [5 empty] | UNDERWAY
| Nr. of other stakeholders receiving information package | 21 | Besides the isntitutions we use the participantes of the courses (more than 10) to dessiminate the strategy | 2 |  | 2 | 5 | 8 | OTHER | 80 | 8 | 20 | 10 | 18 | COMPLETED | COMPLETED | COMPLETED
| Nr. of courses/modules developed for high education professionals | 2 | 2 | 9 | 1 | 1 | 2 | 2 | 10 | 2 | 4 | 3 | 4 | 2 |  |  |  | COMPLETED | UNDERWAY | [6 empty] | COMPLETED
| Nr. of courses/modules developed for high education professionals | 0 | 1 | 3 | 1 | 0 | 2 | 1 | 6 | 0 | 3 | 2 | 1 | 0 | NOT STARTED |  |  |  | NOT STARTED |  |  |  | UNDERWAY |  |  |  | NOT STARTED
| Nr. of courses/modules developed for vocational technicians | 2 | 2 | 3 | 1 | 1 | 2 | 4 | 10 | 2 | 1 | 3 | 1 | 2 | COMPLETED |  |  |  | UNDERWAY |  |  |  | NOT STARTED |  |  | UNDERWAY | COMPLETED
| Nr. of courses/modules implemented for vocational technicians | 0 | 1 | 3 | 1 | 0 | 2 | 0 | 6 | 0 | 1 | 2 | 0 | 2 | NOT STARTED |  |  |  | UNDERWAY |  | NOT STARTED |  |  |  |  | NOT STARTED
OBJECTIVE 2 The Pilot courses/modules and laboratories are supplied with the relevant Software, Tools and Consumables in a timely manner | % of items purchased and used | 0 | 100 | 0 | 100 | 0 | 100 |  |  | 0 | 60 | 100 | 10 | 50 | NOT STARTED | COMPLETED | NOT STARTED |  |  | COMPLETED | UNDERWAY | UNDERWAY | NOT STARTED | UNDERWAY | COMPLETED | UNDERWAY | COMPLETED
OBJECTIVE 4 A quality review of the implemented couses/modules is undertaken including student and course interlocutors feedback with the results analysed and course adjustments implemented, where appropriate | Quality review for each course | NO | YES | NO | YES | NO | NO | NO | YES | NO | NO | YES | NO | YES | NOT STARTED | COMPLETED | UNDERWAY |  | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTER | COMPLETED | NOT STARTED | COMPLETED
| Nr. of staff consulted in review | 0 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 3 |  |  | COMPLETED |  |  | UNDERWAY |  | NOT STARTED |  | UNDERWAY |  | UNDERWAY
| Nr. of students included in review | 0 | 40 | The quality review will take place at the end of the year in December | OTHER | 0 | 0 | 0 | OTHER | 0 | 21 | 81 | 15 | 10 |  |  | NOT STARTED |  |  | NOT STARTED |  | COMPLETED |  | NOT STARTER
| INDICATOR | CHALLENGES Y/N | [12 empty] | CHALLENGES HIGHLIGHT
|  | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR
OBJECTIVE 1 Dissemination of the strategy to stakeholders, donors and training institutions at national level | Information package developed | NO | YES | NO |  | NO | YES | NO | NO | YES | NO | NO | YES | NO |  | ADMINISTRATIVE |  |  |  | FINANCIAL, FORCE MAJEURE |  |  | FINANCIAL |  |  | FINANCIAL, CONTRACT
| Nr. of national training institutions receiving information package | YES | YES | NO |  |  | YES | NO | NO |  |  |  | YES | NO | OTHER | ADMINISTRATIVE |  |  |  | FORCE MAJEURE |  |  | FINANCIAL, FORCE MAJEURE |  |  | ADMIN
| Nr. of other stakeholders receiving information package | YES | YES | NO |  |  | YES | NO | NO |  |  |  | YES | NO | OTHER | OTHER |  |  |  | FORCE MAJEURE |  |  | FINANCIAL |  |  | ADMIN
| Nr. of courses/modules developed | NO | YES | NO | YES | YES | YES | NO | NO | NO |  |  | YES | NO |  | FINANCIAL |  | FINANCIAL | FORCE MAJEURE | FINANCIAL | [5 empty] | CONTRACT
| Nr. of courses/modules implemented | YES | YES | NO | YES | YES | NO | YES | YES | YES | YES |  | YES | YES |  | FINANCIAL |  | FINANCIAL | FORCE MAJEURE |  | FINANCIAL | FINANCIAL | FINANCIAL, FORCE MAJEURE, OTHER | HUMAN RESOURCES |  | CONTRACT, HUMAN RESOURCES | CONTRACT
| Nr. of courses/modules developed | NO | YES | NO | YES | YES | NO | YES | YES |  |  |  | YES | NO |  | FINANCIAL |  | FINANCIAL | FORCE MAJEURE |  | FINANCIAL | FORCE MAJEURE | FINANCIAL | HUMAN RESOURCES |  | n/a
| Nr. of courses/modules implemented | YES | YES | NO | YES | YES | NO | YES | YES |  |  |  | YES | NO | OTHER | FINANCIAL |  | FINANCIAL | FORCE MAJEURE |  | FINANCIAL | OTHER | FINANCIAL, FORCE MAJEURE, OTHER | HUMAN RESOURCES |  | CONTRACT, ADMINISTRATIVE
OBJECTIVE 2 The Pilot courses/modules and laboratories are supplied with the relevant Software, Tools and Consumables in a timely manner | % of items purchased and used | NO | YES | NO | NO |  | YES | YES | YES | YES | YES | NO | YES | YES |  | FINANCIAL |  |  | Delays in procurement and delivry, Delays in procurement and delivery | Delays in procurement and delivry, Delays in procurement and delivery | FINANCIAL | FINANCIAL | FINANCIAL, FORCE MAJEURE, OTHER | FINANCIAL |  | CONTRACT, ADMIN | CONTRACT
OBJECTIVE 4 A quality review of the implemented couses/modules is undertaken including student and course interlocutors feedback with the results analysed and course adjustments implemented, where appropriate | Quality review for each course | NO | YES | NO | YES |  | NO | NO | NO | YES | YES | NO | YES | NO |  | OTHER |  | CONTRACT |  | OTHER | duration to complete the training was short, after approval was given |  | FINANCIAL, FORCE MAJEURE, OTHER | ADMINISTRATIVE |  | ADMIN
| Nr. of staff consulted in review | NO | YES |  | YES |  | NO |  | yes |  |  |  | YES | NO |  | ADMINISTRATIVE |  | CONTRACT |  | OTHER | course facilitators and experts have reviewed the course, | OTHER | FINANCIAL, FORCE MAJEURE, OTHER | CONTRACT |  | ADMIN
| Nr. of students included in review | NO | YES |  | YES |  | NO |  | NO |  |  |  | YES | NO |  | ADMINISTRATIVE |  | CONTRACT |  | OTHER | participant did evaluation of the training (see results attached) |  | FINANCIAL, FORCE MAJEURE, OTHER | RECRUITMENT STUDENTS |  | ADMIN
Mitigation and additional comments - qualitative information
| INDICATOR | MITIGATION
|  | ICPAC | IWEGA | UWC | CSIR | ZAMBIA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR
OBJECTIVE 1 Dissemination of the strategy to stakeholders, donors and training institutions at national level | Information package developed | [5 empty] | Sent the a soft copy of the entire framework | There was no challenge in the dissemination |  | Filling the gap through use of personal resources in order to prevent delay in production of results |  |  | Utilization o institutional funds before receiving transfer from UNESCO
| Nr. of national training institutions receiving information package | [6 empty] | There was no challenge in the dissemination |  | Planning and making personal financial sacrifices pending fund release. |  |  | The activity will be completed when a central workshop is organized. This was pushed to the week starting 1st November 2020
| Nr. of other stakeholders receiving information package | [6 empty] | there was no challenge in the dissemination |  | Awaiting funding |  |  | Reprogramming to the convenience of some stakeholders and key actors
| Nr. of courses/modules developed |  |  |  | In-kind contributions |  | These were already sent | Course materials are been developed |  |  |  |  | Through further engagement, UNESCO agreed to allow one course to be implemented in Uganda
| Nr. of courses/modules implemented |  |  |  | In-kind contributions |  | Done | Procurement process has started to set up eStudio for online training, | Process of engaging partners to increase sporsorship of participants is ongoing | planning for online training | Procurement process has started to set up eStudio for online training, |  | Greenlight was later given by UNESCO which enable us to initiate and implement the course | The cousres were cancelled
| Nr. of courses/modules developed |  |  |  | In-kind contributions |  | Done | Two HND programmes were submitted to National Accreditation and panel report received, (see course details in the attached HCD strategy report) |  | using personal resources | Human Resources & Sanitary constrainsts |  | Not applicable
| Nr. of courses/modules implemented |  |  |  | In-kind contributions |  | Done | Course materials are been developed |  | Staying actions on some of the activities that have security risks | The course materials have been well developed |  | The course was shelved
OBJECTIVE 2 The Pilot courses/modules and laboratories are supplied with the relevant Software, Tools and Consumables in a timely manner | % of items purchased and used | [5 empty] | Used in stock chemicals and instruments to be replaced while awaiting the delivery | Procurement process has started to set up eStudio for online training, |  | using the institutions resources |  |  | We implemented an existin agreement (Framework purchase) between Makerere University and the supplier to atleast obtain a Laptop Computer | Equipment were purchased and used only for the the two TVET level technical courses
OBJECTIVE 4 A quality review of the implemented couses/modules is undertaken including student and course interlocutors feedback with the results analysed and course adjustments implemented, where appropriate | Quality review for each course |  | The course instrutores use part of the course time to dessimnate the strategy. |  | Internal due process followed at CoE |  | Quality review to be undertaken after examinations in December | CoE has undertake the review survey |  | plan for online training |  |  | Not yet planned
| Nr. of staff consulted in review |  |  |  | Internal due process followed at CoE |  | Quality review to be undertaken after examinations in December | CoE has undertaken the quality review survey |  | plan for online training |  |  | Administered and awaiting feedback
| Nr. of students included in review |  |  |  | Internal due process followed at CoE |  | Quality review to be undertaken after examinations in December | CoE has undertaken the quality review survey |  | plan for online training |  |  | Adminsitered electronically

## Course & Modules
|  | COURSE / MODULE TITLE | Theme/s | START | FINISH | TARGET GROUP | LOCATION | MODE OF TEACHING | E-LEARNING PLATFORM | STAFF TRAINING PROVIDED | NUMBER OF PARTICIPANTS |  |  |  | QUALIFICATIONS OF PARTICIPANTS |  |  |  |  | GENDER OF PARTICIPANTS |  | SOURCE OF PARTICPANTS |  |  |  | AGE GROUPS |  |  |  | Quality Review | ADDITIONAL COMMENTS Only if there is anything specific
|  |  |  | DD/MM/YYYY | DD/MM/YYYY | [5 empty] | CEANWATCE | WANWATCE | SANWATCE | OTHER | HIGH SCHOOL | DIPLOMA | BSC | HONOURS | MASTERS | M | F | HIGHER EDUCATION | TVET | PRIVATE | GOVERNMENT | 18-25 | 26-35 | 36-45 | 46-60 | Yes/No
SANWATCE | IWEGA | MAINTENANCE OF NETWORKS AND LOSSES | Water Supply | 07/10/2020 | 13/10/2020 | Junior Technician | Mozambique | FACE 2 FACE | NOT APPLICABLE | NO |  |  | 20 |  |  | 19 | 1 |  | 0 | 11 | 9 |  |  | 13 | 7 | 9 | 7 | 2 | 2 | YES
|  | ENVIRONMENTAL IMPACT ASSESSMENT | Management and Administration | 08/10/2020 | 14/10/2020 | Junior Proffessional | Mozambique | FACE 2 FACE | NOT APPLICABLE | YES |  |  | 21 |  |  | 3 | 14 |  | 4 | 11 | 10 | 7 |  |  | 14 | 1 | 16 | 4 | 0 | YES
| CSIR | EWP221, EWP701 and WAT738 - Application of Academic Knowledge on Water Resource Management (WRM) and Integrated Water Resource Management (IWRM) at the Workplace Environment: Theory and Practice | IWRM | 2020-08-31 | 2020-09-04 | Junior Proffessional | South Africa | E-LEARNING | Google Meet | NOT APPLICABLE |  |  | 124 |  |  |  | 20 | 99 |  | 45 | 77 | not available |  |  |  | 122 | 2 |  |  | YES | (1) Google Meet. (2) Student pool was a post-graduate mix of BSc (Honours) and Masters candidates from different water and environmental disciplines. A total of 115 students were in the email notifications and in attendance. 77 were female and 45 male, with 2 N/R (3)Source of participants is not always clear and determined, although participants did indicate their role in government or civil society (4)The course content was peer reviewed at another university for presentation to Master of Water Science level candidates (5)Student quality review was also administered by UWC after the lecture using a questionnaire developed by UNESCO. Results and analysis of the review were not provided to me.
| UWC | EWP701 Environmental Assessment & Management | Management and Administration | 2020-07-27 | 2020-09-04 | Junior Proffessional | South Africa | E-LEARNING | ZOOM | NOT APPLICABLE |  |  | 20 |  |  |  | 20 |  |  | 7 | 13 |  |  |  |  | 20 | 0 |  |  | NO | We get quality at end of the year
|  | EWP221 Introduction to groundwater hydrology | Groundwater | 2020-07-27 | 2020-09-04 | Junior Proffessional | South Africa | E-LEARNING | ZOOM | NOT APPLICABLE |  |  | 99 |  |  |  |  | 99 |  | 36 | 61 |  |  |  |  | 99 | 0 |  |  | NO | We get quality at end of the year
|  | WAT738 Water Demand Management & Water Security | Water Supply | 2020-08-17 | 2020-09-25 | Junior Proffessional | South Africa | E-LEARNING | ZOOM | NOT APPLICABLE |  |  | 5 | [6 empty] | 2 | 3 |  |  |  |  | 3 | 2 |  |  | NO | We get quality at end of the year
| ZAMBIA | Hydrogeology and Drilling Supervision training | Groundwater | NOT STARTED |  | Senior Technician | Zambia | BLENDED | ZOOM | NOT APPLICABLE
|  | Groundwater and Integrated Water Resources Management in practice (module) | Groundwater | NOT STARTED |  | Junior Proffessional | Zambia
| MALAWI | Hydrological Modelling & Water Quality Modelling | Data and Modelling | 21/09/2020 | 2020-02-10 | Junior Proffessional | Malawi | FACE 2 FACE | NOT APPLICABLE |  |  |  | 6 |  |  |  | 6 |  |  | 3 | 3 | 6 |  |  |  | 6 |  |  |  | NO
|  | Water and Sanitation Systems | Sanitation | 21/09/2020 | 2020-02-10 | Junior Proffessional | Malawi | FACE 2 FACE | NOT APPLICABLE |  |  |  | 10 |  |  |  | 10 |  |  | 7 | 3 | 10 |  |  |  | 3 | 7 |  |  | NO
| BOTSWANA | Principles of Hydrology for Technicians and Artisans | Water Quality | NOT STARTED |  | Junior Technician | Botswana | NOT APPLICABLE
|  | Applied and Field Hydrology for Practitioners | Water Quality | NOT STARTED |  | Senior Technician | Botswana | NOT APPLICABLE
|  | Advanced Hydrology (Young Professionals) | Water Quality | NOT STARTED |  | Junior Proffessional | Botswana | NOT APPLICABLE
|  | Water Resources Management (Young Professionals) | IWRM | NOT STARTED |  | Senior Professionsl | Botswana | NOT APPLICABLE
WANWATCE | KNUST | Sustainable Onsite-Sanitation And Faecal Sludge Management | Sanitation | 31/08/2020 | 17/09/2020 | Junior Proffessional | Ghana | E-LEARNING | ZOOM | NO |  | 62 |  |  | 2 | 8 | 14 |  | 10 | 47 | 15 | 7 | 1 | 6 | 48 | 0 | 18 | 10 | 6
|  | Short course on Water laboratory instrumentation | Water Quality | NOT STARTED |  | Senior Technician | Ghana | BLENDED
|  | Short course on Water systems instrumentation | Water Supply | NOT STARTED |  | Junior Technician | Ghana | BLENDED
|  | Short course on Waste resource recovery innovations and entrepreneurship | Sanitation | NOT STARTED |  | Senior Professionsl | Ghana | BLENDED
|  | Higher National Diploma in Water and Sanitation Engineering | Water Supply | NOT STARTED |  | Junior Technician | Ghana | BLENDED
|  | Higher National Diploma in Instrumentation and Automation Engineering | Water Supply | NOT STARTED |  | Junior Technician | Ghana | BLENDED
| NWRI | BOREHOLE SUPERVISION AND MANAGEMENT | Groundwater | 08/12/2020 | 28/08/2020 | Senior Professionsl | Nigeria | E-LEARNING | ZOOM | YES |  | 68 |  |  |  |  | 68 |  |  | 58 | 10 |  |  |  | 68 |  | 28 | 35 | 5 | YES
|  | BOREHOLE DRILLING | Groundwater | 09/10/2020 | 2020-01-10 | Senior Professionsl | Nigeria | BLENDED | ZOOM | YES |  | 29 |  |  |  |  | 18 | [7 empty] | 18 |  | 4 | 10 | 4 | YES
|  | PLUMBING (HOUSEHOLD WATER MANAGER COURSE) | Water supply | NOT STARTED |  | Junior Technician | Nigeria | BLENDED | SKYPE
|  | INDUCTION COURSE FRESH ENGINEERS AND SCIENTIST IN THE WATER SECTOR | Water Supply | 11.02/202 | 22/12/2020 | Senior Professionsl | Nigeria | BLENDED | ZOOM | YES |  | 15 |  |  |  |  | 15 | [7 empty] | 15 |  | 15 |  |  | YES
|  | BILLING AND REVENUE GENERATION MANAGEMENT | Management and Administration | 21/09/2020 | 16/10/2020 | Senior Professionsl | Nigeria | BLENDED | SKYPE | YES |  | 8 |  |  |  |  | 8 |  |  | 6 | 2 |  |  |  | 8 |  |  | 8 |  | YES
|  | PLANT AND EQUIPMENT MAINTENANCE | Water Supply | 21/09/2020 | 16/10/2020 | Junior Proffessional | Nigeria | BLENDED | SKYPE | YES |  | 6 |  |  |  | 6 |  |  |  | 6 | 0 |  |  |  | 6 |  |  | 6 |  | YES
|  | WATER NETWORK MODELLING, NETWORK O&M, NON-REVENUE WATER MANAGEMENT AND LEAK DETECTION | Data and Modelling | 19/10/2020 | 13/11/2020 | Senior Professionsl | Nigeria | BLENDED | SKYPE | YES |  | 6 |  |  |  |  | 6 |  |  | 6 | 0 |  |  |  | 6 |  |  | 4 | 2 | YES
|  | WATER TREATMENT, PRODUCTION PROCESSES AND OPTIMIZATION, WTP OPERATION AND MAINTENANCE | Water quality | 19/10/2020 | 13/11/2020 | Senior Professionsl | Nigeria | BLENDED | SKYPE | YES |  | 5 |  |  |  |  | 5 |  |  | 5 | 0 |  |  |  | 5 |  |  | 3 | 2 | YES
|  | WATER WELL DRILLING | Groundwater | NOT STARTED |  | Junior Technician | Nigeria | BLENDED | ZOOM | YES
|  | WELDING AND RIG FABRICATION | Groundwater | NOT STARTED |  | Junior Technician | Nigeria | BLENDED | ZOOM | YES
| BENIN | Water Supply and Environmental Engineering | Water Supply | NOT STARTED |  |  | Nigeria | NOT APPLICABLE
|  | Remote Sensing and GIS | Data and Modelling | NOT STARTED |  |  | Nigeria | NOT APPLICABLE
|  | Borehole Construction and Maintenance | Groundwater | NOT STARTED |  |  | Nigeria | NOT APPLICABLE
|  | Operation and Maintenance of Water Distribution System | Water Supply | NOT STARTED |  |  | Nigeria | NOT APPLICABLE
| UCAD | Project Management in the Water Sector | Management and Administration | 2020-09-14 | 2020-10-16 | Senior Professionsl | Senegal | E-LEARNING | TEAMS | NOT APPLICABLE |  | 63 |  |  | 0 | 0 | 10 |  | 53 | 38 | 25 | 39 | 10 | 6 | 8 | 15 | 26 | 17 | 5 |  | Information on participant characteristics is not always complete. An additional effort to complete it is underway. The course was organized in a quasi-emergency situation.
|  | GIS and Remote Sensing technologies applied to Water and Sanitation Management | Data and Modelling | 2020-10-15 | 2020-10-30 | Junior Proffessional | Senegal | BLENDED | TEAMS | NOT APPLICABLE |  | 39 |  |  | 0 | 0 | 9 |  | 21 | 27 | 12 | 27 | 4 | 2 | 6 | 8 | 13 | 15 | 3 |  | Information on participant characteristics is not always complete. An additional effort to complete it is underway. The course was organized in a quasi-emergency situation.
|  | Hydrological Modelling using SWAT | Data and Modelling | 2020-10-12 | 2020-10-29 | Junior Technician | Senegal | BLENDED | TEAMS | NOT APPLICABLE |  | 30 |  |  | 0 | 2 | 8 |  | 20 | 22 | 8 | 25 | 2 | 0 | 3 | 10 | 6 | 12 | 2
|  | Introduction to UAV photogrammetry | Data and Modelling | 2020-10-14 | 2020-11-07 | Junior Proffessional | Senegal | BLENDED | TEAMS | NOT APPLICABLE |  | 28 |  |  | 0 | 4 | 5 |  | 19 | 18 | 10 | 20 | 3 | 0 | 5 | 15 | 7 | 5 | 1
CEANWATCE | Khartoum | Data Acquisition in Water Resources Management | Data and Modelling | 22/11/2019 | 2/1/21020 | Junior Proffessional | Sudan | FACE 2 FACE | NOT APPLICABLE | NOT APPLICABLE | 42 | 0 | 0 | 0 | 0 | 0 | 18 |  | 24 | 18 | 24 | 17 | 0 | 10 | 15 | 11 | 20 | 9 | 2 | YES | 42 participants from CEANWATCE
|  | Water, Sanitation and Hygiene (WASH) | Sanitation | 01/05/2020 | 16/1/2020 | Junior Proffessional | Sudan | FACE 2 FACE | NOT APPLICABLE | NOT APPLICABLE | 30 | 0 | 0 | 0 | 0 | 0 | 15 |  | 15 | 12 | 18 | 9 | 0 | 9 | 12 | 7 | 12 | 10 | 1 | YES
|  | Data Acquisition in Surface and Ground Water | Data and Modelling | 19/1/2020 | 30/01/2020 | Senior Technician | Sudan | FACE 2 FACE | NOT APPLICABLE | NOT APPLICABLE | 22 | 0 | 0 | 0 | 0 | 5 | 12 |  | 5 | 10 | 12 | 8 | 6 | 0 | 8 | 3 | 11 | 7 | 1 | YES
|  | Water Quality Monitoring and Testing | Water Quality | 16/02/2020 | 27/02/2020 | Senior Technician | Sudan | FACE 2 FACE | NOT APPLICABLE | NOT APPLICABLE | 26 | 0 | 0 | 0 | 0 | 3 | 8 |  | 15 | 9 | 17 | 9 | 8 | 0 | 9 | 2 | 8 | 8 | 8 | YES
| Makerere | Water Diplomacy and Negotiation | Management and Administration | 14/10/2020 | 21/10/2020 | Senior Professionsl | Uganda | BLENDED | ZOOM | NOT APPLICABLE | 31 | [5 empty] | 17 |  | 14 | 16 | 15 | 5 |  |  | 26 |  | 8 | 18 | 5 | YES | Quality review in terms of evaluation
| EIWR | Operational Hydrology: Flow and Sediment monitoring in streams | Data and Modelling | 2020-10-01 | 13/01/2020 | Senior Technician | Ethiopia | FACE 2 FACE | NOT APPLICABLE | NOT APPLICABLE | 12 | 0 | 0 | 0 | 0 | 0 | 10 |  | 2 | 10 | 2 | 0 | 1 | 0 | 11 | 2 | 8 | 2 | 0 | YES
|  | Irrigation Systems Diagnosis, On-farm Water Management, Operation and Maintenance | Water Supply | 14/1/2020 | 18/01/2020 | Senior Technician | Ethiopia | FACE 2 FACE | NOT APPLICABLE | NOT APPLICABLE | 12 | 0 | 0 | 0 | 0 | 0 | 10 |  | 2 | 10 | 2 | 0 | 1 | 0 | 11 | 2 | 8 | 2 | 0 | YES
|  | Surface Water Resources Assessment Using Advanced Modeling Techniques | Data and Modelling | NOT STARTED |  | Senior Technician | Ethiopia | BLENDED | ZOOM | NOT APPLICABLE |  | 0 |  |  | 0 | 0
|  | Water Productivity and Irrigation Systems Modelling | Water Supply | NOT STARTED |  | Senior Technician | Ethiopia | BLENDED | ZOOM | NOT APPLICABLE |  | 0 |  |  | 0 | 0
| ICPAC | Data Management (GIS and Remote Sensing ) | Data and Modelling | NOT STARTED |  | Junior Proffessional | Kenya | FACE 2 FACE | NOT APPLICABLE
|  | Early Warning Systems (Climate variability & change ) | Data and Modelling | NOT STARTED |  | Junior Proffessional | Kenya | E-LEARNING
|  | Write the title of the course or module in full |  | Add the start date of the course in the format provided | Add the finish date of the course in the format provided | Use the drop down box and choose from one of the four target groups | Use the drop down box and select the country the course is being held in | How was the course provided: Face2Face, Blended or E-Learning? | If you choose OTHER, please add name of the teaching platform in the additional comments column | Choose YES or NO only for BLENDED OR E-LEARNING courses/modules. If only Face 2 Face training was provided, then choose NOT APPLICABLE | Use the drop down box to enter the number of students from the region which includes Kenya, Uganda, Ethiopia and Sudan | Use the drop down box to enter the number of students from the region which includes Nigeria, Ghana and Senegal | Use the drop down box to enter the number of students from the region which includes South Africa, Botswana, Malawi, Mozambique and Zambia | Choose from the drop down box the number of students not from one of the recognised regions. | Use the drop down box to enter the number of students with this qualification | Use the drop down box to enter the number of students with this qualification | Use the drop down box to enter the number of students with this qualification |  | Use the drop down box to enter the number of students with this qualification | Use the drop down box to enter the number of students who are MALE | Use the drop down box to enter the number of students who are FEMALE | Use the drop down box to enter the number of students from Higher Education: College or University (public or private) | Use the drop down box to enter the number of students from TVET | Use the drop down box to enter the number of students from the private sector including small medium enterprises, artisinal businesses etc. but excluding excluding HE/TVET facilities | Use the drop down box to enter the number of students from government departments | Use the drop down box to enter the number of students in this age range | Use the drop down box to enter the number of students in this age range | Use the drop down box to enter the number of students in this age range | Use the drop down box to enter the number of students in this age range | Use the drop down list to indicate if a course/module has undergone a quality review | Add additional information here. For example where you have chosen other in the drop down box add the country, age, location etc. which is relevant.

## Gender & Course thematic
THEME | SANWATCE |  | WANWATCE |  | CEANWATCE |  | Sub-Total |  | TOTAL
| Male | Female | Male | Female | Male | Female | Male | Female
Mgmt. & Admin. | 18 | 23 | 44 | 27 | 16 | 15 | 78 | 65 | 143
IWRM | 45 | 77 | 0 | 0 | 0 | 0 | 45 | 77 | 122
Groundwater | 36 | 61 | 58 | 10 | 0 | 0 | 94 | 71 | 165
Water Supply | 13 | 12 | 6 | 0 | 10 | 2 | 29 | 14 | 43
Sanitation | 7 | 3 | 47 | 15 | 12 | 18 | 66 | 36 | 102
Water Quality | 0 | 0 | 5 | 0 | 9 | 17 | 14 | 17 | 31
Data and Modelling | 3 | 3 | 73 | 30 | 38 | 38 | 114 | 71 | 185
TOTAL | 122 | 179 | 233 | 82 | 85 | 90 | 440 | 351 | 791

## Course & Module Themes
Illustrative list of courses
Institution | Course title
IWEGA | Environmental Impact Assessment
CSIR | Integrated Water Resource Management (IWRM) at the Workplace Environment: Theory and Practice
UWC | Introduction to groundwater hydrology
MALAWI | Hydrological Modelling & Water Quality Modelling
KNUST | Short course on Sustainable Onsite-Sanitation And Faecal Sludge Management
NWRI | Billing and Revenue Generation Management
Water Network Modeling, Network O&M, Non-Revenue Water Management and Leak Detection
Water Treatment, Production Processes and Optimization, WTP Operation and Maintenance
UCAD | GIS and Remote Sensing Technologies Applied to Water and Sanitation Management
Project Management in the Water Sector
KHARTOUM | Data Acquisition in Water Resources Management
Water, Sanitation and Hygiene (WASH)
MAKERERE | Water Diplomacy and Negotiation
EIWR | Operational Hydrology: Flow and Sediment Monitoring in Streams
Irrigation Systems Diagnosis, On-farm Water Management, Operation and Maintenance
Implemented
|  | IMPLEMENTED | IWEGA | CSIR | UWC | ZAMBIA | MALAWI | BOTSWANA | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | ICPAC | EIWR | TOTAL
|  | Management and Administration | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 5
|  | IWRM | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Groundwater | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  | Water Supply | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 5
|  | Sanitation | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2
|  | Water Quality | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2
|  | Data and Modelling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 7
|  | TOTAL | 2 | 1 | 3 | 0 | 2 | 0 | 1 | 7 | 0 | 4 | 4 | 1 | 0 | 2 | 27
Developed
|  | DEVELOPED | IWEGA | CSIR | UWC | ZAMBIA | MALAWI | BOTSWANA | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | ICPAC | EIWR | TOTAL
|  | Management and Administration | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 5
|  | IWRM | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  | Groundwater | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 8
|  | Water Supply | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | 12
|  | Sanitation | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4
|  | Water Quality | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 6
|  | Data and Modelling | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 2 | 0 | 2 | 2 | 12
|  | TOTAL | 2 | 1 | 3 | 2 | 2 | 4 | 6 | 10 | 4 | 4 | 4 | 1 | 2 | 4 | 49

## Participants M-F
CoE | PARTICIPANTS
| Total number | SANWATCE % |  | WANTWATCE % |  | CEANWATCE %
|  | Male | Female | Male | Female | Male | Female
IWEGA | 41 | 55 | 45
CSIR | 122 | 37 | 63
UWC | 122 | 37 | 63
MALAWI | 16 | 64 | 36
KNUST | 62 |  |  | 76 | 24
NWRI | 93 |  |  | 87 | 13
UCAD | 160 |  |  | 67 | 33
KHARTOUM | 120 |  |  |  |  | 41 | 59
MAKERERE | 31 |  |  |  |  | 53 | 47
EIWR | 24 |  |  |  |  | 83 | 17
TOTAL | 791
[9 empty] | Male | Female
| SANWATCE % | WANWATCE % | CEANWATCE % |  |  |  |  | Total Global | 61 | 39
Male | 48 | 77 | 59 | 184
Female | 52 | 23 | 41 | 116

## Target group
Target Group | IWEGA | CSIR | UWC | ZAMBIA | BOTSWANA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC
Junior Professional | 1 | 1 | 3 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 13
Senior Professional | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 0 | 1 | 0 | 0 | 8
Junior Technician | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2
Senior Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 4
TOTAL | 2 | 1 | 3 | 0 | 0 | 2 | 1 | 7 | 0 | 4 | 4 | 1 | 2 | 0 | 27
[16 empty] | TARGET GROUP | SANWATCE | WANWATCE | CEANWATCE | TOTAL
[16 empty] | Junior professional | 7 | 4 | 2 | 13
[16 empty] | Senior professional | 0 | 7 | 1 | 8
[16 empty] | Junior technician | 1 | 1 | 0 | 2
[16 empty] | Senior technician | 0 | 0 | 4 | 4
[16 empty] | TOTAL | 8 | 12 | 7 | 27

## Mode of Teaching
Mode of Teaching | SANWATCE |  |  |  |  | WANWATCE |  |  |  | CEANWATCE |  |  |  | TOTAL
| IWEGA | CSIR | UWC | ZAMBIA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC
Face-to-face | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 10
Blended | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 3 | 0 | 1 | 0 | 0 | 10
E-learning | 0 | 1 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 7
TOTAL | 2 | 1 | 3 | 0 | 2 | 1 | 7 | 0 | 4 | 4 | 1 | 2 | 0 | 27
[6 empty] | I removed the courses not implemented yet | [8 empty] | MODE OF TEACHING | SANWATCE | WANWATCE | CEANWATCE | TOTAL
[15 empty] | Face-to-face | 4 | 0 | 6 | 10
[15 empty] | Blended | 0 | 5 | 1 | 6
[15 empty] | E-learning | 4 | 7 | 0 | 11
[15 empty] | TOTAL | 8 | 12 | 7 | 27

## E-learning platform
E-LEARNING PLATFORMS | SANWATCE |  | WANWATCE |  |  | CEANWATCE | TOTAL
| CSIR | UWC | KNUST | NWRI | UCAD | MAKERERE
Zoom | 0 | 3 | 1 | 3 | 0 | 1 | 8
Microsoft Teams | 0 | 0 | 0 | 0 | 4 | 0 | 4
Skype | 0 | 0 | 0 | 4 | 0 | 0 | 4
Google Meet | 1 | 0 | 0 | 0 | 0 | 0 | 1
TOTAL | 1 | 3 | 1 | 7 | 4 | 1 | 17
[8 empty] | E-LEARNING PLATFORM | SANWATCE | WANWATCE | CEANWATCE | TOTAL
[8 empty] | Zoom | 3 | 4 | 1 | 8
[8 empty] | Microsoft Teams | 0 | 4 | 0 | 4
[8 empty] | Skype | 0 | 4 | 0 | 4
[8 empty] | Google Meet | 1 | 0 | 0 | 1
[8 empty] | TOTAL | 4 | 12 | 1 | 17

## Mode of Teaching & Age
MODE OF TEACHING | AGE GROUP OF PARTICIPANTS
| SANWATCE |  |  |  | WANWATCE |  |  |  | CEANWATCE |  |  |  | Sub-Total |  |  |  | TOTAL
| 18-25 | 26-35 | 36-45 | 46-60 | 18-25 | 26-35 | 36-45 | 46-60 | 18-25 | 26-35 | 36-45 | 46-60 | 18-25 | 26-35 | 36-45 | 46-60
Face-to-face | 19 | 30 | 6 | 2 | 0 | 0 | 0 | 0 | 27 | 67 | 38 | 12 | 46 | 97 | 44 | 14 | 201
Blended | 0 | 0 | 0 | 0 | 33 | 45 | 63 | 14 | 0 | 8 | 18 | 5 | 33 | 53 | 81 | 19 | 186
E-learning | 244 | 4 | 0 | 0 | 15 | 72 | 62 | 16 | 0 | 0 | 0 | 0 | 259 | 76 | 62 | 16 | 413
TOTAL | 263 | 34 | 6 | 2 | 48 | 117 | 125 | 30 | 27 | 75 | 56 | 17 | 338 | 226 | 187 | 49 | 800

## Participants - theme
| COURSE PARTICIPANTS | [13 empty] | TOTAL
COURSE THEME | IWEGA | CSIR | UWC | ZAMBIA | MALAWI | BOTSWANA | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC
Mgmt. & Admin | 21 | 0 | 20 | 0 | 0 | 0 | 0 | 8 | 0 | 63 | 0 | 31 | 0 | 0 | 143
IWRM | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124
Groundwater | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 196
Water Supply | 20 | 0 | 5 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 12 | 0 | 58
Sanitation | 0 | 0 | 0 | 0 | 10 | 0 | 62 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 102
Water Quality | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 26 | 0 | 0 | 0 | 31
Data & Modelling | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 97 | 64 | 0 | 12 | 0 | 185
TOTAL | 41 | 124 | 124 | 0 | 16 | 0 | 62 | 137 | 0 | 160 | 120 | 31 | 24 | 0 | 839
[16 empty] | COURSE THEME | COURSE PARTICIPANTS |  |  | TOTAL
[17 empty] | SANWATCE | WANWATCE | CEANWATCE
[16 empty] | Mgmt. & Admin | 41 | 71 | 31 | 143
[16 empty] | IWRM | 124 | 0 | 0 | 124
[16 empty] | Groundwater | 99 | 97 | 0 | 196
[16 empty] | Water Supply | 25 | 21 | 12 | 58
[16 empty] | Sanitation | 10 | 62 | 30 | 102
[16 empty] | Water Quality | 0 | 5 | 26 | 31
[16 empty] | Data & Modelling | 6 | 103 | 76 | 185
[16 empty] | TOTAL | 305 | 359 | 175 | 839

## Gender & Target Groups
TARGET GROUP | SANWATCE |  | WANWATCE |  | CEANWATCE |  | Sub-Total |  | TOTAL
| Male | Female | Male | Female | Male | Female | Male | Female
Junior professional | 111 | 170 | 98 | 37 | 30 | 42 | 239 | 249 | 488
Senior professional | 0 | 0 | 113 | 37 | 16 | 15 | 129 | 52 | 181
Junior technician | 11 | 9 | 22 | 8 | 0 | 0 | 33 | 17 | 50
Senior technician | 0 | 0 | 0 | 0 | 39 | 33 | 39 | 33 | 72
TOTAL | 122 | 179 | 233 | 82 | 85 | 90 | 440 | 351 | 791

## Source of participants
SOURCE | IWEGA | CSIR | UWC | ZAMBIA | BOTSWANA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | TOTAL | [6 empty] | SOURCE | SANWATCE |  | WANWATCE |  |  | CEANWATCE |  |  | TOTAL
Higher Education | 7 | not available | not available | 0 | 0 | 16 | 7 | 0 | 0 | 111 | 43 | 5 | 0 | 0 | 189 | [7 empty] | IWEGA | MALAWI | KNUST | NWRI | UCAD | KHARTOUM | MAKERERE | EIWR
TVET | 0 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 19 | 14 | 0 | 2 | 0 | 36 | [6 empty] | Higher Education | 7 | 16 | 7 | 0 | 111 | 43 | 5 | 30 | 219
Private | 13 |  |  | 0 | 0 | 0 | 6 | 0 | 0 | 8 | 19 | 0 | 0 | 0 | 46 | [6 empty] | TVET | 0 | 0 | 1 | 0 | 19 | 14 | 0 | 2 | 36
Government | 21 |  |  | 0 | 0 | 0 | 48 | 126 | 0 | 22 | 44 | 26 | 22 | 0 | 309 | [6 empty] | Private | 13 | 0 | 6 | 0 | 8 | 19 | 0 | 0 | 46
TOTAL | 41 | 0 | 0 | 0 | 0 | 16 | 62 | 126 | 0 | 160 | 120 | 31 | 24 | 0 | 580 | [6 empty] | Government | 21 | 0 | 48 | 126 | 22 | 44 | 26 | 42 | 329
[22 empty] | TOTAL | 41 | 16 | 62 | 126 | 160 | 120 | 31 | 74 | 630
[16 empty] | REGION | HIGHER EDUCATION | TVET | Private | Government | TOTAL
[16 empty] | SANWATCE | 23 |  | 13 | 21 | 57
[16 empty] | WANWATCE | 118 | 20 | 14 | 196 | 348
[16 empty] | CEANWATCE | 78 | 16 | 19 | 112 | 225
[16 empty] | TOTAL | 219 | 36 | 46 | 329 | 630

## Participant Qualifications
QUALIFICATION | IWEGA | CSIR | UWC | ZAMBIA | BOTSWANA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | TOTAL
High School | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Diploma | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 6 | 8 | 0 | 0 | 0 | 50
BSc. (incl. Honours) | 15 | 119 | 119 | 0 | 0 | 16 | 14 | 120 | 0 | 32 | 53 | 17 | 20 | 0 | 525
Masters | 4 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 113 | 59 | 14 | 4 | 0 | 204
TOTAL | 41 | 119 | 119 | 0 | 0 | 16 | 34 | 126 | 0 | 151 | 120 | 31 | 24 | 0 | 781
[16 empty] | CoE | High School | Diploma | BSc. (incl. Honours) | Masters | TOTAL
[16 empty] | SANWATCE | 0 | 22 | 269 | 4 | 295
[16 empty] | WANWATCE | 2 | 20 | 166 | 123 | 311
[16 empty] | CEANWATCE | 0 | 8 | 90 | 77 | 175
[16 empty] | TOTAL | 2 | 50 | 525 | 204 | 781

## Age Groups
AGE GROUP | IWEGA | CSIR | UWC | ZAMBIA | BOTSWANA | MALAWI | KNUST | NWRI | BENIN | UCAD | KHARTOUM | MAKERERE | EIWR | ICPAC | TOTAL
18-25 | 10 | 122 | 122 | 0 | 0 | 9 | 0 | 0 | 0 | 48 | 23 | 0 | 4 | 0 | 338
26-35 | 23 | 2 | 2 | 0 | 0 | 7 | 18 | 47 | 0 | 52 | 51 | 8 | 16 | 0 | 226
36-45 | 6 | 0 | 0 | 0 | 0 | 0 | 10 | 66 | 0 | 49 | 34 | 18 | 4 | 0 | 187
46-60 | 2 | 0 | 0 | 0 | 0 | 0 | 6 | 13 | 0 | 11 | 12 | 5 | 0 | 0 | 49
TOTAL | 41 | 124 | 124 | 0 | 0 | 16 | 34 | 126 | 0 | 160 | 120 | 31 | 24 | 0 | 800
[16 empty] | CoE | AGE GROUPS |  |  |  | TOTAL
[17 empty] | 18-25 | 26-35 | 36-45 | 46-60
[16 empty] | SANWATCE | 263 | 34 | 6 | 2 | 305
[16 empty] | WANWATCE | 48 | 117 | 125 | 30 | 320
[16 empty] | CEANWATCE | 27 | 75 | 56 | 17 | 175
[16 empty] | TOTAL | 338 | 226 | 187 | 49 | 800

## Costs
|  | GOODS SUPPLIES SERVICES |  |  | HUMAN RESOURCES |  |  | REGION | GOODS SUPPLIES SERVICES |  | TOTAL | HUMAN RESOURCES |  | TOTAL
|  | Preparation | Delivery | TOTAL | Preparation | Delivery | TOTAL |  | Preparation | Delivery |  | Preparation | Delivery
SANWATCE | IWEGA | 11.14 | 5113.8 | 5113.8 | 1500 | 9154 | 10654 | SANWATCE | 11.14 | 16013.8 | 16024.94 | 26561.15 | 35187.55 | 61748.7
| CSIR | 0 | 3900 | 3900 | 4800 | 4800 | 9600 | WANWATCE | 22274 | 85203 | 107477 | 36400 | 55750 | 92150
| UWC | 0 | 0 | 0 | 9661.15 | 12079.55 | 21740.6975 | CEANWATCE | 632 | 36405.8889 | 37037.8889 | 27000 | 43572.57 | 70572.57
| ZAMBIA | 0 | 0 | 0 | 0 | 0 | 0 | TOTAL | 22917.14 | 137622.6889 | 160539.8289 | 89961.15 | 134510.12 | 224471.27
| BOTSWANA | 0 | 0 | 0 | 10000 | 0 | 10000
| MALAWI | 0 | 7000 | 7000 | 600 | 9154 | 16754
WANWATCE | KNUST | 0 | 19000 | 19000 | 2400 | 6000 | 11700
| NWRI | 15500 | 62000 | 43200 | 12000 | 44500 | 56500
| BENIN | 0 | 0 | 0 | 6000 | 0 | 6000
| UCAD | 6774 | 4203 | 10977 | 16000 | 5250 | 11250
CEANWATCE | KHARTOUM | 0 | 22609.8889 | 22609.8889 | 8400 | 13400 | 21800
| MAKERERE | 532 | 9496 | 12639 | 7100 | 9366.67 | 16466.6667
| EIWR | 100 | 4300 | 4400 | 11500 | 20805.9 | 32305.9
| TOTAL | 22917.14 | 137622.6889 | 128839.6889 | 89961.15 | 134510.12 | 224771.2642