**NEPAD SANWATCE**

**EU JRC PROJECT**

**IMPORTANT DATES**

|  |  |  |
| --- | --- | --- |
| **TASK** | **DUE DATE** | **LEAD INSTITUTION** |
| **DELIVERABLE 1 to JRC** |
| JLP 1.1 SURVEY ON REQUIREMENTS IN HIGHER EDUCATION AND WITHIN TRAININGS FOR PRACTITIONERS IN THE WATER SECTOR | End Feb. 2012 | SU |
| JLP 1.2. STUDY ON HOW THE CENTRES OF EXCELLENCE COULD BETTER ADDRESS SECTOR EXPERTISE FOR CONSULTANCY AND ADVOCACY NEEDS FOR WATER SECTOR | End Feb. 2012 | SU |
| KM 2.1 ANALYSIS OF THE AQUAKNOW USERS AND POLICY MAKERS | End Feb. 2012 | UBotswana; UWC; |
| **SUBMIT DELIVERABLE 1 TO JRC due end Feb. 2012** |
| **DELIVERABLE 2 to JRC** |
| KM2.2 DEVELOPING A LIST OF ACTIONS AND CHANNELS FOR THE DISSEMINATION AND DISSEMINATION MATERIAL | Mid March 2012 | UZambia |
| JLP 1.3 PREPARATION OF MECHANISMS FOR DIALOGUE, AWARENESS RAISING AND COACHING ELEMENTS | Mid April 2012 | UWC |
| **SUBMIT DELIVERABLE 2 TO JRC end April 2012** |
| **DELIVERABLE 3 to JRC** |
| KM2.3 PRODUCE EDUCATIONAL MATERIAL, LINKED WITH AQUAKNOW PLATFORM AND DEVELOPMENT OF COURSES | Early to mid May 2012 | UKZN – NEW LEAD TO BE ASSIGNED |
| JLP 1.4 CONSULTATIVE PLANNING SEMINAR in Botswana | Preliminary dates:13-14 June 2012 or 20-21 June 2012. | UBotswana |
| JLP 1.5 FINAL DESIGN OF THE SEMINARS AND TRAININGS | Mid to end July 2012 | CSIR |
| JLP 1.6TRAINING/SEMINARS | August 2012 | ALL |
| JLP 1.7 PROCEEDINGS AND FEEDBACK MATERIAL FROM THE TRAININGS/SEMINARS | August 2012 during 1.6 training seminars | SU |
| JLP 1.8 AMCOW AND SADC REPORTS | Date to be determined by AMCOW | SU |
| KM2.4 INTERNATIONAL WORKSHOP | Date to be confirmed by JRC | UMalawi |
| KM 2.5 E-CONFERENCE AND THE PROCEEDINGS OF THE E-CONFERENCE | Early to mid October 2012 | SU |
| **SUBMIT DELIVERABLE 3 TO JRC due end Oct 2012** |
| **DELIVERABLE 4 to JRC** |
| **CONTRACTUAL REPORTS** | End Nov. 2012 | SU |
| **SUBMIT DELIVERABLE 4 TO JRC due end Nov 2012** |
| PROJECT CONCLUDE |